Verify access supplier(Leitungslieferant) should display as "OXGG" | OS-56129 | 4-Minor |  | Wave 9.1
Verify Rollout status (Ausbaustatus) should display - notPlanned (grey),areaPlanned (grey),preMarketing (yellow-grey),underConstruction (yellow-grey),homesPassed (orange),homesPassedPlus (orange),homesPrepared (green),homesReady | OS-56128 | 4-Minor |  | Wave 9.1
Check :Glasfaser Detailinformationen" section and Checkserviceability response includes FTTH-OXG details | OS-56127 | 4-Minor |  | Wave 9.1
Check serviceability information (coming from VFP) VFPGlasfaser Regio Klasse ,Project Reference,Downstream/Upstream (speed),Leitungslieferant (Access Supplier),Ausbaus Status,Vermarktungsphase,Roll-out End Date | OS-56126 | 4-Minor |  | Wave 9.1
Clicks on 'i' button to see more information about the Serviceability | OS-56125 | 4-Minor |  | Wave 9.1
See availability of FTTH OXG at a given address The Serviceability status (green/orange/yellow-grey) should displayed as it does for FTTH-DG based on priority of FTTH-L2-BSA/OXGG. | OS-56124 | 4-Minor |  | Wave 9.1
Verify Checkserviceability response for FTTH-L2-BSA technology and Access Supplier is OXGG | OS-56123 | 4-Minor |  | Wave 9.1
Search the FTTH address and perform the checkservisability | OS-56121 | 4-Minor |  | Wave 9.1
Login into Omnius Telesales channel | OS-56120 | 4-Minor |  | Wave 9.1
Check archive logs request and Response for the checkServiceability | OS-56116 | 4-Minor |  | Wave 9.1
Verify When the CheckServiceability/Reference_Serviceability contains the presales and Redensifcation phases Omnius has to display 'Geplanter Ausbautermin'(Rollout end date) | OS-56115 | 4-Minor |  | Wave 9.1
Verify sales_phase Vermarktungsphase should display value (e.g., "Vorvermarktung", "Nachverdichtung", "Regelvermarktung"). | OS-56114 | 4-Minor |  | Wave 9.1
Verify Project reference should disaply FTTH-L2-BSA/OXG | OS-56113 | 4-Minor |  | Wave 9.1
Verify access supplier(Leitungslieferant) should display as "OXGG" | OS-56112 | 4-Minor |  | Wave 9.1
Verify Rollout status (Ausbaustatus) should display - notPlanned (grey),areaPlanned (grey),preMarketing (yellow-grey),underConstruction (yellow-grey),homesPassed (orange),homesPassedPlus (orange),homesPrepared (green),homesReady | OS-56111 | 4-Minor |  | Wave 9.1
Check :Glasfaser Detailinformationen" section and Checkserviceability response includes FTTH-OXG details. | OS-56109 | 4-Minor |  | Wave 9.1
Check serviceability information (coming from VFP) VFPGlasfaser Regio Klasse ,Project Reference,Downstream/Upstream (speed),Leitungslieferant (Access Supplier),Ausbaus Status,Vermarktungsphase,Roll-out End Date | OS-56108 | 4-Minor |  | Wave 9.1
Clicks on 'i' button to see more information about the Serviceability | OS-56107 | 4-Minor |  | Wave 9.1
ee availability of FTTH OXG at a given address The Serviceability status (green/orange/yellow-grey) should displayed as it does for FTTH-DG based on priority of FTTH-L2-BSA/OXGG | OS-56106 | 4-Minor |  | Wave 9.1
Verify Checkserviceability response for FTTH-L2-BSA technology and Access Supplier is OXGG | OS-56105 | 4-Minor |  | Wave 9.1
Search the FTTH address and perform the checkservisability | OS-56104 | 4-Minor |  | Wave 9.1
Login into Omnius Retail channel | OS-56103 | 4-Minor |  | Wave 9.1
INT ¦¦ SCN_12 ¦¦Verify all OGW validations for CreateFNPOrder API and OM's SendDocument API | OS-56102 | 4-Minor |  | Wave 9.1
INT ¦¦ SCN_11 ¦¦ Telesales/Retail Perform Technology change to FTTH - DSL/LTE ZH > FTTH OXG ONLY when phase = GREEN | OS-56101 | 4-Minor |  | Wave 9.1 | [5 empty] | 24/Jul/24 1:40 PM;pallavi.chaudhari1@vodafone.com;Not able to test in SIT env due to test data is not available.;;;
INT ¦¦ SCN_10 ¦¦ Omnius Perform Move offnet Cable, FTTB > FTTH OXG ONLY when phase = GREEN | OS-56088 | 4-Minor |  | Wave 9.1 | [5 empty] | 24/Jul/24 1:40 PM;pallavi.chaudhari1@vodafone.com;Not able to test in SIT env due to test data is not available.;;;
INT ¦¦ SCN_09¦¦ Telesales/Retail Perform ILS (Package change) ONLY when phase = GREEN | OS-56085 | 4-Minor |  | Wave 9.1 | [5 empty] | 24/Jul/24 1:39 PM;pallavi.chaudhari1@vodafone.com;Not able to test in SIT env due to test data is not available.;;;
INT ¦¦ SCN_08 ¦¦Telesales perform New acq submit order for Fibre products with the Access supplier,Home-ID, Rollout_Status & SALES_PHASE to OGW in Generate Contract/Fullfillment mode | OS-56084 | 4-Minor |  | Wave 9.1
INT ¦¦ SCN_07 ¦¦Retail perform New acq submit order for Fibre products with the Access supplier,Home-ID, Rollout_Status & SALES_PHASE to OGW in Generate Contract/Fullfillment mode | OS-56083 | 4-Minor |  | Wave 9.1
INT ¦¦ SCN_06¦¦ Verify Wish-Date logic for Availability Color Green for FTTH-L2-BSA | OS-56081 | 4-Minor |  | Wave 9.1
INT ¦¦ SCN_05 ¦¦ Validate captured Home-ID of the customer in the Checkout for FTTH OXG and Passed to OGW | OS-56079 | 4-Minor |  | Wave 9.1
INT ¦¦ SCN_04 ¦¦Telesales Perform Checkservisability for FTTH OXG availability | OS-56076 | 4-Minor |  | Wave 9.1
INT ¦¦ SCN_03 ¦¦ Retail Perform Checkservisability for FTTH OXG availability | OS-56075 | 4-Minor |  | Wave 9.1
Verify WS and WF logs and check order should be submitted to backend | OS-56074 | 4-Minor |  | Wave 9.1
Submit the order | OS-56073 | 4-Minor |  | Wave 9.1
Generate the contract summary | OS-56072 | 4-Minor |  | Wave 9.1
Fill all the required details | OS-56071 | 4-Minor |  | Wave 9.1
Click on Zum Checkout | OS-56070 | 4-Minor |  | Wave 9.1
Click on weiter button | OS-56069 | 4-Minor |  | Wave 9.1
Add Cable product in shopping cart from configurator | OS-56068 | 4-Minor |  | Wave 9.1
Select the Cable package | OS-56067 | 4-Minor |  | Wave 9.1
Perform checkservisibility for Cable address | OS-56066 | 4-Minor |  | Wave 9.1
Login into Telesales/Retail channel | OS-56065 | 4-Minor |  | Wave 9.1
Verify WS and WF logs and check order should be submitted to backend | OS-56064 | 4-Minor |  | Wave 9.1
Submit the order | OS-56063 | 4-Minor |  | Wave 9.1
Generate the contract summary | OS-56062 | 4-Minor |  | Wave 9.1
Fill all the required details | OS-56061 | 4-Minor |  | Wave 9.1
Click on Zum Checkout | OS-56060 | 4-Minor |  | Wave 9.1
Click on weiter Button | OS-56059 | 4-Minor |  | Wave 9.1
Add DSL product in shopping cart from configurator | OS-56058 | 4-Minor |  | Wave 9.1
Select the DSL package | OS-56057 | 4-Minor |  | Wave 9.1
Perform checkservisibility for DSL address | OS-56056 | 4-Minor |  | Wave 9.1
Login into Telesales/Retail channel | OS-56055 | 4-Minor |  | Wave 9.1
INT ¦¦ SCN_02 ¦¦ Retail/Telesales perform regression for Cable order | OS-56054 | 4-Minor |  | Wave 9.1
INT ¦¦ SCN_01 ¦¦ Retail/Telesales perform regression for DSL order | OS-56053 | 4-Minor |  | Wave 9.1
SIT5 ENV Telesales and Retail ¦ ACQ flow -Getting Service error at customer details page | OS-56002 | 1-Blocker | Environment issue | Wave 9.1 | Getting service error while perorming ACQ flow mobile postpaid scenario as a part of Sanity testing on SIT5 ENV, both Telesales and Retail channels Steps to reproduce the issue. # Login to Telesales or Retail channel on SIT5 ENV # Perform serviceability check # or skip the 2nd step directly select the HW and tariff for mobile postpaid ACQ flow # add the HW and tariff into the shopping cart # click on zumcheckout button on checkout page # Enter all the customer details fields at customer section page # click on weiter button Actual result: Service error Ein Servicefehler ist aufgetreten. Versuchen Sie es später noch einmal. DETAILED INFORMATION RetrieveIdentificationMethods Service war nicht erfolgreich : <env:Fault xmlnenv="http://schemas.xmlsoap.org/soap/envelope/"><faultcode>env:Server </faultcode><faultstring>&lt;WebServiceUALException&gt;&lt;n:ROOT xmlnn='http://amdocs/iam/api/GeneralResponse' xmlnxsi='http://www.w3.org/2001/XMLSchema-instance'&gt;&lt;Event/&gt;&lt;Error&gt;&lt;Number&gt;JESIERR-1&lt;/Number&gt;&lt;Description&gt;amdocs.ecommerce.common.exceptions.SystemException&lt;/Description&gt;&lt;/Error&gt;&lt;/n:ROOT&gt;&lt;/WebServiceUALException&gt;</faultstring><faultactor>VFDEGetIdentMethodsEG</faultactor><detail><ual:WebServiceUALException type="xsd:string" xmlnual="http://amdocs/vfde/ident/VFDEGetIdentMethods" xmlnxsi="http://www.w3.org/2001/XMLSchema-instance">Code=JESIERR-1:Description=amdocs.ecommerce.common.exceptions.SystemException</ual:WebServiceUALException></detail> </env:Fault> !image-2024-05-16-13-18-34-953.png! Expected result: We should not get any error messge and able to proceed further steps PFA | Environment issue | Mobile | OGW | Amdocs -> OGW | 17/May/24 1:43 PM;bharath.krishnamurthy@vodafone.com;[~ankesh.anurag@vodafone.com] [~pallavi.chaudhari1@vodafone.com] Hi Ankesh, Any updates on this issue?;;; 21/May/24 8:55 AM;ankesh.anurag@vodafone.com;Hi [~bharath.krishnamurthy@vodafone.com] , which wave it is on SIT5? I can see that it is down. Please check with SIT team to deploy a proper build. Let me know if after deployment also you are facing issue? !image-2024-05-21-12-22-17-454.png¦width=878,height=197!;;; 24/May/24 11:26 AM;bharath.krishnamurthy@vodafone.com;[~pallavi.chaudhari1@vodafone.com], [~sudhanshu.shekhar@vodafone.com] [~gaurav.chauhan4@vodafone.com] [~ankesh.anurag@vodafone.com] Hi All, Getting this error while accessing SIT5 Env, Retail channel !image-2024-05-24-14-54-36-499.png! Kein Zugriff auf diese Store-Ansicht No access to this store view but the same credentials working fine for SIT5 Env, Telesales channel !image-2024-05-24-14-56-36-609.png! PFA;;; 24/May/24 11:39 AM;bharath.krishnamurthy@vodafone.com;[~pallavi.chaudhari1@vodafone.com], [~sudhanshu.shekhar@vodafone.com] [~gaurav.chauhan4@vodafone.com] [~ankesh.anurag@vodafone.com] Hi All, Working fine with user name as retail-agent , for SIT5 Retail Channel !image-2024-05-24-15-09-10-905.png! PFA v9.20.0-BSNAPSHOT9.20.0 2024-05-14 10:15 ;;; 24/May/24 11:50 AM;bharath.krishnamurthy@vodafone.com;[~pallavi.chaudhari1@vodafone.com], [~sudhanshu.shekhar@vodafone.com] [~gaurav.chauhan4@vodafone.com] [~ankesh.anurag@vodafone.com] Hi All, retested the scenario on SIT5 ENV, Retail Channel with user name as retail-agent v9.20.0-BSNAPSHOT9.20.0 2024-05-14 10:15 Working fine now till this step, Contract Summary document is getting created. Order ID: 20146 !image-2024-05-24-15-19-56-802.png! !image-2024-05-24-15-20-02-305.png! PFA;;;
INT Test Plan ¦ OS-41783¦¦Lead Management Read and Edit - PPM718201 Lead Management Integration Phase 4 | OS-55911 | 4-Minor | Cancelled | Wave 9.1 | Please refer: https://jira.sp.vodafone.com/browse/OS-41783 |  |  |  | Amdocs -> OGW | 17/Jul/24 2:20 PM;bhavika.kohale@vodafone.com;Duplicate. ;;;
INT Test Plan ¦¦ OS-49954 ¦¦ eSIM Push (part 2) - PPM 541076 | OS-55910 | 4-Minor |  | Wave 9.1 | Please refer:https://jira.sp.vodafone.com/browse/OS-49954 |  |  |  | Amdocs -> OGW
INT- TestPlan ¦ OS-47654 ¦¦Show and administrate existing subscribers with Device Financing Tariffs in OSF (Phase 1) | OS-55909 | 4-Minor |  | Wave 9.1 | https://jira.sp.vodafone.com/browse/OS-57006 Please refer above testplan |  |  |  | Amdocs -> OGW
INT - Testplan ¦¦ OS-34593 ¦¦ Matrix FTTB OXG in OSF (PPM ID: 654569) | OS-55894 | 4-Minor |  | Wave 9.1 | For details like Goal, description etc. please refer Epic https://jira.sp.vodafone.com/browse/OS-34593 |  |  |  |  | 31/Jul/24 7:42 PM;horst.froehlich@vodafone.com;VF decided to cancel FTTB OXG because no longer business relevant. Therefore 2 not yet processed scenarios (SCN_07 and SCN_08) marked as "not applicable" and will not be processed.;;;
INT - Testplan ¦¦ OS-27236 ¦¦ Matrix - FTTH OXG IT Interim solution (PPM ID 660854) | OS-55892 | 4-Minor |  | Wave 9.1 | For details like Goal, description etc. please refer Epic [https://jira.sp.vodafone.com/browse/OS-27236]
INT ¦ Apply filter combinations by A)number B)Date c)Remark | OS-55705 | 4-Minor |  | Wave 9.1
INT ¦ Go to hamburger menu in top left side | OS-55704 | 4-Minor |  | Wave 9.1
INT ¦ In connection details add vanity number | OS-55697 | 4-Minor |  | Wave 9.1
INT ¦ Verify reserved number is not shown. | OS-55695 | 4-Minor |  | Wave 9.1
INT ¦¦ In connection details click on Change provider (Anbieter wechseln) | OS-55694 | 4-Minor |  | Wave 9.1
INT ¦ Add the reserve number FROM RESERVED LIST. | OS-55693 | 4-Minor |  | Wave 9.1
INT ¦verify Omnius will not save the Reserved Phone Number(s) with Checkout data which Omnius uses to pre-fill when Agent re-opens the saved Cart. | OS-55679 | 4-Minor |  | Wave 9.1
INT ¦Again Perform test step 6 to 9. | OS-55678 | 4-Minor |  | Wave 9.1
INT ¦ Reopen the shopping cart by searching mobile number. | OS-55677 | 4-Minor |  | Wave 9.1
INT ¦ Click Save and send shopping cart. | OS-55676 | 4-Minor |  | Wave 9.1
INT ¦ click on Return to Shopping Cart" (Zurück zum Warenkorb). | OS-55675 | 4-Minor |  | Wave 9.1
INT ¦ click on weiter. | OS-55674 | 4-Minor |  | Wave 9.1
INT ¦ Select the reserve number from list. | OS-55673 | 4-Minor |  | Wave 9.1
INT ¦¦ Select two SOHO with rv mobile package. | OS-55671 | 4-Minor |  | Wave 9.1
INT ¦¦ Verify agent cannot see the input field “Reserved phone number” in the connection data section with label “Reservierte Rufnummer (optional)” | OS-55667 | 4-Minor |  | Wave 9.1
INT ¦¦ verify agent cannot see a new checkbox “reserved phone number” between the “save cart” and “proceed to checkout” buttons and select it. | OS-55666 | 4-Minor |  | Wave 9.1
INT ¦¦ Go to hamburger menu in top left side and verify phone number list view is not shown. | OS-55665 | 4-Minor |  | Wave 9.1
INT ¦ verify in fulfillment mode 'MSISDN' ( field name in request payload) updated in EAI- KIAS ActivateSubscriber interface. | OS-55646 | 4-Minor |  | Wave 9.1
INT ¦¦ Verify in Fulfillment mode subscriber Number provided in subscriber list with relation to order line. SubmitOrderRequest->DATA->SubscriberList->SubscriberDetails->SubscriberNumber | OS-55645 | 4-Minor |  | Wave 9.1
INT ¦¦ .verify in generatemcontract mode 'SubscriberNumber' ( field name in request payload) updated in OM 'Generate Contract' interface. | OS-55644 | 4-Minor |  | Wave 9.1
INT ¦ in Generate contract mode verify Subscriber Number provided in subscriber list with relation to order line. (SubmitOrderRequest->DATA->SubscriberList->SubscriberDetails->SubscriberNumber) | OS-55643 | 4-Minor |  | Wave 9.1
INT ¦¦ Verify Omnius populate "Reserved Phone Number" in ProcessOrder Request (Generate Contract and Fulfillment mode) that captured by Agent in Checkout->Connection Data section. | OS-55642 | 4-Minor |  | Wave 9.1 | (XML Path: ProcessOrderRequest/SalesOrder/LogicalPackage[*]/Subscriber/Ctn/PhoneNumber)
INT ¦ Verify new interface RetrieveAvailableNumberBlocks is called. | OS-55641 | 4-Minor |  | Wave 9.1
INT ¦¦ Fetch and verify logs. | OS-55640 | 4-Minor |  | Wave 9.1
INT ¦ Verify Reserved Phone Number is displayed in the Order Manager Detailed Overview page . | OS-55639 | 4-Minor |  | Wave 9.1
INT ¦ Submit Order . | OS-55638 | 4-Minor |  | Wave 9.1
INT ¦ Verify reserved munber is shown in contract document and not in CS | OS-55637 | 4-Minor |  | Wave 9.1
INT ¦ Click on druken to generate document. | OS-55636 | 4-Minor |  | Wave 9.1
INT ¦ Manually add the reserve number. | OS-55635 | 4-Minor |  | Wave 9.1
INT ¦ Verify agent can see the input field “Reserved phone number” in the connection data section with label “Reservierte Rufnummer (optional)” | OS-55634 | 4-Minor |  | Wave 9.1
INT ¦verify agent can see a new checkbox “reserved phone number” between the “save cart” and “proceed to checkout” buttons and select it. | OS-55629 | 4-Minor |  | Wave 9.1
INT ¦ Move to extended shopping cart. | OS-55628 | 4-Minor |  | Wave 9.1
INT ¦Select hw/tariff. | OS-55627 | 4-Minor |  | Wave 9.1
INT ¦ Select SOHO with rv mobile package. | OS-55626 | 4-Minor |  | Wave 9.1
INT ¦¦search a number. | OS-55625 | 4-Minor |  | Wave 9.1
INT ¦¦ Go to hamburger menu in top left side and select phone number list view. | OS-55624 | 4-Minor |  | Wave 9.1
INT ¦¦ login to retail channel | OS-55623 | 4-Minor |  | Wave 9.1
INT ¦¦ SC_10 ¦¦ UI VALIDATION: Hamburger Menu filter Combination | OS-55618 | 4-Minor |  | Wave 9.1 |  |  |  |  | Amdocs
INT ¦¦ SC_09 ¦¦ Run Retail Soho B and enter Vanity Number (Wunschrufnummer)" input field, then Omnius will disable the "Reserved Phone Number" | OS-55617 | 4-Minor |  | Wave 9.1 |  |  |  |  | Amdocs
INT ¦¦ SC_08 ¦¦ Run Retail Change provider (Anbieter wechseln) FLOW to verify Reserved number is disabled | OS-55615 | 4-Minor |  | Wave 9.1 |  |  |  |  | Amdocs
INT ¦¦ SC_07 ¦¦ RETAIL - Soho type B select checkbox in extended shopping and select reserved phone-no from phone number list | OS-55613 | 4-Minor |  | Wave 9.1 |  |  |  |  | Amdocs
INT ¦¦ SC_06 ¦¦ RETAIL - Soho type B save a cart and remove saved Reserved Phone Number(s) and flag status while saving the Cart so that number(s) are released to reuse again | OS-55600 | 4-Minor |  | Wave 9.1 |  |  |  |  | Amdocs
INT ¦¦ SC_05 ¦¦ RETAIL - Soho type B with RV with 2 mobile packages | OS-55599 | 4-Minor |  | Wave 9.1 |  |  |  |  | Amdocs
INT ¦¦ SC_04 ¦¦ RETAIL - Soho type B w/o RV without selecting reversed number BAU | OS-55598 | 4-Minor |  | Wave 9.1 |  |  |  |  | Amdocs
INT ¦¦ SC_03 ¦¦ RETAIL - Soho type B with RV | OS-55572 | 4-Minor |  | Wave 9.1 |  |  |  |  | Amdocs
INT ¦¦ SC_02 ¦¦ RETAIL - Soho type B w/o RV disable permission BAU | OS-55571 | 4-Minor |  | Wave 9.1 |  |  |  |  | Amdocs
INT ¦¦ SC_01 ¦¦ RETAIL: Soho type s with rv select reseverved number from hamburger and manually add it in connection details | OS-55570 | 4-Minor |  | Wave 9.1
INT Testplan ¦¦ CR 786 - SOHO - Access to reserved phone number blocks | OS-55552 | 4-Minor |  | Wave 9.1 | Please Refer -https://jira.sp.vodafone.com/browse/OS-39851 |  |  |  | Amdocs
verify in WF logs that an additional field pastObjectContractChanges with subfields pastObjectContractEndDate, pastObjectCategory, pastObjectCategoryPresentationText should be added in buildingInfo call. | OS-55178 | 4-Minor |  | Wave 9.1
verify the OGW logs | OS-55177 | 4-Minor |  | Wave 9.1
submit the order | OS-55176 | 4-Minor |  | Wave 9.1
click on weiter button and proceed | OS-55175 | 4-Minor |  | Wave 9.1
click on packet andern button | OS-55174 | 4-Minor |  | Wave 9.1
Search and load cable customer | OS-55173 | 4-Minor |  | Wave 9.1
Login to telesale channel | OS-55172 | 4-Minor |  | Wave 9.1
verify in WF logs that an additional field pastObjectContractChanges with subfields pastObjectContractEndDate, pastObjectCategory, pastObjectCategoryPresentationText should be added in buildingInfo call. | OS-55170 | 4-Minor |  | Wave 9.1
verify the OGW logs | OS-55169 | 4-Minor |  | Wave 9.1
submit the order | OS-55168 | 4-Minor |  | Wave 9.1
click on weiter button and proceed | OS-55167 | 4-Minor |  | Wave 9.1
click on packet andern button | OS-55166 | 4-Minor |  | Wave 9.1
Search and load cable customer | OS-55165 | 4-Minor |  | Wave 9.1
Login to retail channel | OS-55164 | 4-Minor |  | Wave 9.1
SC_1¦¦Retail¦¦Perform_customer_search. | OS-55163 | 4-Minor |  | Wave 9.1 |  |  |  |  | Amdocs
INT - Testplan ¦¦ CR787 ¦¦ Futurize - Show MNV enddate of already contractless buildings | OS-55162 | 4-Minor |  | Wave 9.1 | The additional information will be available through the buildingInfo endpoint of VKDGateway. An additional field pastObjectContractChanges with subfields pastObjectContractEndDate, pastObjectCategory, pastObjectCategoryPresentationText will be added. h3. 1.1.1 As Is Situation OGW doesn’t receive the pastObejctContractChange information from VKD hence send it to Omnius subsequently part of GetProductAvailability call. h3. 1.1.1 Desired Situation OGW will send the new object – pastObejctContractChange in response object towards Omnius as received from VKD via VKD_LOC/buildingInfo call. |  |  |  | Amdocs -> OGW
INT - Testplan ¦¦ CR767 ¦¦ Correct Legal Partner for Kabelunabhängie Dienste (KUD) to Vodafone Deutschland GmbH | OS-55091 | 4-Minor |  | Wave 9.1 | For more info please refer to https://jira.sp.vodafone.com/browse/FAST-739
SIT1 ¦¦ Retail/Telesales ¦¦ For FTTH order getting product selection error on Zum Checkout | OS-52410 | 1-Blocker | Fixed | Wave 9.0 Wave 9.1 | Steps To Reproduced:- 1.Place the stub file for checkservisability on Omnius path /var/SP/data/omnius/osf-telesales-sit1/var/stubs/default/Vfde/Address/Checkservisability 2.Login into Omnius Telesales/Retail 3.search the address 3.add the Glasfaser product 4.Click on ZUmcheckout Actual Result:- Getting product selection error on ZumCheckout Expected Result:- Order should able to procced with selected product | After Omnius deployment it is working fine |  | Omnius | TechM -> OSE | 27/Feb/24 2:31 PM;pallavi.chaudhari1@vodafone.com;Retest is blocked due to OS-52412;;; 27/Feb/24 4:26 PM;ariadne.thun1@vodafone.com;[~pallavi.chaudhari1@vodafone.com] but this ticket here OS-52410 was fixed? Then we should have it in status resolved, if its ready for retest - even when retest is blocked ;;; 08/Mar/24 1:29 PM;pallavi.chaudhari1@vodafone.com;It is working fine now ;;;
INT - TestPlan ¦¦ OS-12184 ¦ SOL1SE32 - Introduce Hardware order incl HW only order-2 | OS-52142 | 4-Minor |  | Wave 9.1 | Please Refer Epic: [https://jira.sp.vodafone.com/browse/OS-12184]